## Risk Register
Project Title: National Flood Forecasting and Warning Service (NFFWS )
Project Stage: Stage 1
Theme | Item | Description of Risk | Owner | Initial Risk Level | Measures to reduce/mitigate risk | Residual Risk Level | Status
Staffing | 1.1 | Health emergency (e.g. COVID-19) causes significant absence of key staff in Met Éireann and the OPW. | OPW, ME | L | Backup staff roles identified, procedures documented and training manuals in place. | L
Staffing | 1.2 | Difficulties in recruitment of specialist staff (backfills and new posts) due to market conditions | OPW, ME | M | Engage with D/PER on conditions and PAS on targetted campaigns, Contract out some of the work to third parties (e.g. coastal modelling) | L
Technical | 2.1 | Failure of OPW water level and flow data sharing infrastructure and ICT Systems (e.g. waterlevel.ie) | OPW | M | Implement technical solutions such as roaming SIM cards with static IP addresses. Install fixed telephone and power lines. Increase staffing to ensure reduced chance of failure and quicker response time. | L
Technical | 2.2 | Failure of critical ICT infrastructure in FFC | ME | M | (text required regarding business continuity or backup planning etc.)
Communications | 3.1 | Unrealistic expectations of the service amongst stakeholders - There may be an expectation that the NFFWS will be able to accurately forecast all types of flooding for all circumstances | OPW, ME | H | Manage Communications to highlight what the limitations of the service will be (i.e does not include small catchments/waves/pluvial flooding/groundwater flooding etc. | M - L
Policy and Governance | 4.1 | Delays in definition of Stage 2 | OPW, ME | L | Build consensus through consultation and engagement with all relevant stakeholders Allocation of necessary resources | L
Policy and Governance | 4.2 | Government approval and funding for proposed approach to Stage 2 not forthcoming or delayed | OPW, DHLGH | M | Communication with D/PER and the political system | L
Risk Level Options
Low
Medium
High