## Risk Register
Project Title: National Flood Forecasting and Warning Service (NFFWS )
Project Stage: Stage 1
Associated Theme or Task | Item | Identified by | Description of Risk | Initial Risk Level | Measures to reduce/mitigate risk | Residual Risk Level | Status
COVID-19 | 1.1 | OPW | Inability to travel to International venues for related training (e.g. Met Eireann unable to attend training at IMDC in Europe).
| 1.2 | OPW | Delays in regular/ongoing training events e.g. EFAS User Group Meeting.
| 1.3 | OPW | Inability to carry out site inspections at existing and proposed gauge locations.
| 1.4 | ME | 24 hour on call – a reduced number of Hydrometeorologists to provide this support due to illness | L | There are 6 Hydrometeorologists on call. Plus there is the Chief Hydrometeorologist and an ex member of the FFC that can provide support. | L
| 1.5 | ME | Hydrological Models Development – if the designated staff fall ill there would be issues in maintaining the progress of the work | L | Three staff have worked on this project and have developed memorandums and scripts that their colleagues could follow and continue with the work. | L
| 1.6 | ME | TSSF Transfer Trial – if Chief Hydrometeorologists were to fall ill there would be issues in maintaining the progress of the work | M | The Chief Hydrometeorologist currently is the only FFC member with the skills to work on this project. A second member of staff is being trained up in Linux and scripting. | L
| 1.7 | ME | FEWS – if the designated staff fall ill there would be issues in developing a tender | L | Three staff have worked on this project and have developed memorandums and scripts that their colleagues could follow and continue with the work. | L
Others recently added: | 1.8 | OPW | Failure to recruit all necessary staff in OPW | H | Contract out some of the work to third parties (e.g. coastal modelling) | M
| 1.9 | OPW | Failure of water level and flow data sharing infrastructure and IT Systems (e.g. waterlevel.ie) | M | Implement technical solutions such as roaming SIM cards with static IP addresses. Install fixed telephone and power lines. Increase staffing to ensure reduced chance of failure and quicker response time. | L
| 1.1 | OPW | Failure to install monitoring equipment that is necessary to support the needs of the NFFWS | H | Accurately assess the monitoring requirements and develop a plan for intsallation of relevant gauges. Investigate workarounds for model development in poorly gauged areas. | M - L
| 1.11 | OPW | Delays relating to the legal considerations of the Service | M | Set up working group to progress this work Procure external legal expertise | L
| 1.12 | OPW | Unrealistic expectations of the service amongst stakeholders and the general public - There may be an expectation that the NFFWS will be able to accurately forecast all types of flooding for all circumstances | H | Through Public awareness campaigns make it clear what the service can and cannot do. Manage Communications to highlight what the limitations of the service will be (i.e does not include small catchments/pluvial flooding/groundwater flooding etc. | M - L
| 1.13 | ME | Failure to recruit all necessary staff in Met Éireann | M | Continue to work with Departmental HR and PAS to recruit new hydrometeorologists. | L
Risk Level Options
Low
Medium
High