## Risk Register
Project Title: National Flood Forecasting and Warning Service (NFFWS )
Project Stage: Stage 1
Theme | Item | Description of Risk | Owner | Initial Risk Level | Measures to reduce/mitigate risk | Residual Risk Level | Status
Staffing | 1.1 | Health emergency (e.g. COVID-19) causes significant absence of key staff in Met Éireann and the OPW. | OPW, ME | L | Backup staff roles identified, procedures documented and training manuals in place. | L
Staffing | 1.2 | Difficulties in recruitment of specialist staff (backfills and new posts) due to market conditions | OPW, ME | M | Engage with D/PER on conditions and PAS on targetted campaigns, Contract out some of the work to third parties (e.g. coastal modelling) | L
Technical | 2.1 | Failure of OPW water level and flow data sharing infrastructure and ICT Systems (e.g. waterlevel.ie) | OPW | M | Implement technical solutions such as roaming SIM cards with static IP addresses. Install fixed telephone and power lines. Increase staffing to ensure reduced chance of failure and quicker response time. | L
Technical | 2.2 | Failure of critical ICT infrastructure in FFC | ME | L | Both the IFICS and Delft-FEWS systems, which support flood forecasting communications and fluvial forecasting respectively, are cloud based, have back-up systems and are geo resilient. They are both supported by their respective contractors via an on-call facility. The fluvial forecast system also incorporates a number of process fallbacks. The TSSF model is run on the ECMWF’s HPC facility. It’s operation is monitored by staff at ECMWF. All staff of the FFC have been given training on troubleshooting the model and documentation has been developed to support monitoring and maintenance. The relevant vendors have been made aware that the FFC will be providing an enhanced service. | L
Communications | 3.1 | Unrealistic expectations of the service amongst stakeholders - There may be an expectation that the NFFWS will be able to accurately forecast all types of flooding for all circumstances | OPW, ME | H | Manage Communications to highlight what the limitations of the service will be (i.e does not include small catchments/waves/pluvial flooding/groundwater flooding etc. | M - L
Policy and Governance | 4.1 | Delays in definition of Stage 2 | OPW, ME | M | Build consensus through consultation and engagement with all relevant stakeholders Allocation of necessary resources | M
Policy and Governance | 4.2 | Government approval and funding for proposed approach to Stage 2 not forthcoming or delayed | OPW, DHLGH | M | Communication with D/PER and the political system | L
Risk Level Options
Low
Medium
High